## Product Backlog
BANKING ACTIVITY SIMULATION PLATFORM PRODUCT BACKLOG
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Setup project structure and Spring Boot development environment | MUST HAVE | -- | Jaknam Sahithi | 3- Completed
Sprint 1 | Sprint 1 | US-02 | Understand Spring Boot, Maven, JPA and H2 database concepts | SHOULD HAVE | -- | Jaknam Sahithi | 3- Completed
Sprint 1 | Sprint 1 | US-03 | Design Account model, project architecture and package structure | MUST HAVE | US-02 | Jaknam Sahithi | 3- Completed
Sprint 2 | Sprint 2 | US-04 | Implement Account JPA entity and H2 in-memory database setup | MUST HAVE | US-03 | Jaknam Sahithi | 3- Completed
Sprint 2 | Sprint 2 | US-05 | Implement AccountRepository using Spring Data JPA | MUST HAVE | US-04 | Jaknam Sahithi | 3- Completed
Sprint 2 | Sprint 2 | US-06 | Implement AccountService with create account and get account APIs | MUST HAVE | US-05 | Jaknam Sahithi | 3- Completed
Sprint 3 | Sprint 3 | US-07 | Implement deposit and withdrawal transaction functionality | MUST HAVE | US-06 | Jaknam Sahithi | 3- Completed
Sprint 3 | Sprint 3 | US-08 | Implement fund transfer between accounts | MUST HAVE | US-07 | Jaknam Sahithi | 3- Completed
Sprint 3 | Sprint 3 | US-09 | Add transaction validations and global exception handling | MUST HAVE | US-07 | Jaknam Sahithi | 3- Completed
Sprint 3 | Sprint 3 | US-10 | Implement Transaction model and TransactionRepository | MUST HAVE | US-08 | Jaknam Sahithi | 3- Completed
Sprint 4 | Sprint 4 | US-11 | Implement AlertService for low balance email notifications | SHOULD HAVE | US-07 | Jaknam Sahithi | 3- Completed
Sprint 4 | Sprint 4 | US-12 | Implement ReportService for file-based transaction logging | SHOULD HAVE | US-10 | Jaknam Sahithi | 3- Completed
Sprint 4 | Sprint 4 | US-13 | Write unit tests for service layer using JUnit 5 and Mockito | MUST HAVE | US-10 | Jaknam Sahithi | 3- Completed
Sprint 5 | Sprint 5 | US-14 | Develop frontend UI - HTML5 structure and layout | SHOULD HAVE | -- | Jaknam Sahithi | 3- Completed
Sprint 5 | Sprint 5 | US-15 | Add JavaScript with Fetch API for REST backend calls | MUST HAVE | US-14 | Jaknam Sahithi | 3- Completed
Sprint 5 | Sprint 5 | US-16 | Add professional CSS3 styling and responsive design | MUST HAVE | US-14 | Jaknam Sahithi | 3- Completed
Sprint 6 | Sprint 6 | US-17 | Integrate frontend with Spring Boot REST APIs | MUST HAVE | US-15 | Jaknam Sahithi | 3- Completed
Sprint 6 | Sprint 6 | US-18 | Implement Simulation engine for bulk random transaction generation | SHOULD HAVE | US-13 | Jaknam Sahithi | 3- Completed
Sprint 6 | Sprint 6 | US-19 | Perform end-to-end testing and push project to GitHub | SHOULD HAVE | US-17 | Jaknam Sahithi | 2- In Progress

## Sprint Backlog
BANKING ACTIVITY SIMULATION PLATFORM SPRINT BACKLOG
NOTE: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Estimate (Hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-01 | 1 | Introduction to Project (Banking Activity Simulation Platform) | 16-Feb-26 | 16-Feb-26 | Jaknam Sahithi | Knowledge Transfer | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | 2 | Study Spring Boot, Maven, JPA and H2 database fundamentals | 17-Feb-26 | 17-Feb-26 | Jaknam Sahithi | Tech Training | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | 3 | Document discussion and architectural design review | 18-Feb-26 | 22-Feb-26 | Jaknam Sahithi | Analysis | Completed | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-04 | 4 | Account JPA entity design and H2 database configuration | 23-Feb-26 | 25-Feb-26 | Jaknam Sahithi | System Design | Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | 5 | Implementation of AccountRepository and Spring Data JPA | 26-Feb-26 | 28-Feb-26 | Jaknam Sahithi | Backend Dev | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | 6 | AccountService implementation, list all accounts and error handling | 01-Mar-26 | 03-Mar-26 | Jaknam Sahithi | Error Handling | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-07 | 7 | Backend workflow analysis for transactions and debugging | 04-Mar-26 | 07-Mar-26 | Jaknam Sahithi | Debugging | Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | 8 | Development of deposit, withdrawal and transfer methods | 08-Mar-26 | 12-Mar-26 | Jaknam Sahithi | Backend Dev | Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | 9 | Global exception handler and transaction validation logic | 13-Mar-26 | 15-Mar-26 | Jaknam Sahithi | Coding | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | 10 | Transaction model, TransactionRepository and integration review | 16-Mar-26 | 16-Mar-26 | Jaknam Sahithi | Testing | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-11 | 11 | AlertService and Spring Mail library integration | 17-Mar-26 | 18-Mar-26 | Jaknam Sahithi | Coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | 12 | ReportService for file-based transaction logging | 17-Mar-26 | 18-Mar-26 | Jaknam Sahithi | Coding | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | 13 | Unit testing - AccountService, TransactionService, Controller | 17-Mar-26 | 19-Mar-26 | Jaknam Sahithi | Testing | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 5 BACKLOG
US-14 | 14 | Develop frontend UI - HTML5 structure and forms | 20-Mar-26 | 22-Mar-26 | Jaknam Sahithi | Coding | Completed | 5 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | 15 | Add JavaScript Fetch API calls for all REST endpoints | 23-Mar-26 | 27-Mar-26 | Jaknam Sahithi | Coding | Completed | 4 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | 16 | Add professional CSS3 styling and responsive layout | 28-Mar-26 | 31-Mar-26 | Jaknam Sahithi | Coding | Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 6 BACKLOG
US-17 | 17 | Integrate frontend with Spring Boot backend REST APIs | 01-Apr-26 | 02-Apr-26 | Jaknam Sahithi | API Integration | Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | 18 | Implement Simulation engine and Transaction Stats API | 01-Apr-26 | 10-Apr-26 | Jaknam Sahithi | Coding | Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | 19 | End-to-end testing, GitHub push and final review | 11-Apr-26 | 21-Apr-26 | Jaknam Sahithi | Deployment | In Progress | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
BANKING ACTIVITY SIMULATION PLATFORM STAND UP MEETING LOG
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Confusion about Spring Boot project setup and Maven configuration | Mentor clarified project requirements, tech stack and development environment setup
Sprint 1 | Day 3 | Doubts regarding Eclipse IDE setup and Spring Boot project import process | Attended mentor sessions and practiced Maven import steps before starting development
Sprint 2 | Day 10 | Difficulty in designing the Account JPA entity and H2 database relationships | Discussed JPA entity design with mentor and reviewed Spring Data JPA documentation
Sprint 2 | Day 16 | Encountered errors while implementing AccountRepository with H2 in-memory database | Reviewed H2 configuration in application.properties and resolved JDBC connection issues
Sprint 3 | Day 20 | Difficulty in debugging transaction logic for deposit and withdrawal operations | Attended backend classes and traced execution flow using Eclipse debugger
Sprint 3 | Day 27 | Delay in completing fund transfer functionality and exception handling implementation | Extended work hours and implemented GlobalExceptionHandler to resolve all errors
Sprint 4 | Day 30 | AlertService not triggering emails - Spring Mail SMTP misconfiguration issue | Imported correct Jakarta Mail dependency and fixed SMTP settings in application.properties
Sprint 4 | Day 34 | Some JUnit 5 unit tests failing due to incorrect Mockito mock setup | Reviewed Mockito configuration, fixed mock return values and re-ran all service layer tests
Sprint 5 | Day 40 | Frontend UI alignment and layout issues across different browser window sizes | Adjusted CSS flexbox layout and fixed margin and padding inconsistencies across all sections
Sprint 6 | Day 44 | Frontend Fetch API calls returning CORS errors when connecting to Spring Boot backend | Added CorsConfig class in Spring Boot to allow all origins and resolved integration errors

## Retrospection
BANKING ACTIVITY SIMULATION PLATFORM SPRINT RETROSPECTION
SL # | Sprint # | Sprint Start Date | Sprint End Date | Team Member Name | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 16-Feb-26 | 22-Feb-26 | Jaknam Sahithi | Clarify Spring Boot project requirements and setup with mentor before starting | Directly starting coding without reading documentation | Attending mentor sessions to gain knowledge on Spring Boot and Maven | Practiced Spring Boot setup and reviewed project requirements with mentor
2 | Sprint 2 | 23-Feb-26 | 03-Mar-26 | Jaknam Sahithi | Implement Account module with proper JPA entity design and H2 configuration | Implementing entities without verifying database design first | Reviewing and debugging errors collaboratively with mentor | Discussed JPA entity design with mentor before implementation
3 | Sprint 3 | 04-Mar-26 | 16-Mar-26 | Jaknam Sahithi | Attend debugging sessions and plan time for transaction and transfer methods | Delaying exception handling implementation until the last moment | Attending backend classes to understand transaction flow and logic | Attended classes and extended work hours to complete transfer functionality
4 | Sprint 4 | 17-Mar-26 | 19-Mar-26 | Jaknam Sahithi | Import and verify required Spring Mail libraries before starting AlertService | Skipping library and dependency checks before module implementation | Reviewing module integration before running JUnit 5 unit tests | Imported Jakarta Mail libraries and fixed SMTP configuration
5 | Sprint 5 | 20-Mar-26 | 31-Mar-26 | Jaknam Sahithi | Check UI alignment and Fetch API integration early in frontend development | Leaving CSS alignment and JS integration issues unaddressed until the end | Using CSS flexbox for layout and alignment fixes across all sections | Fixed all UI alignment issues using CSS and connected all Fetch API endpoints
6 | Sprint 6 | 01-Apr-26 | 21-Apr-26 | Jaknam Sahithi | Perform CORS configuration and integration testing between frontend and backend early | Deferring integration testing and GitHub push to the very end of the sprint | Systematic end-to-end bug fixing and GitHub version control practices | Performed full integration testing, fixed CORS errors and pushed project to GitHub